## L2R DE Process RACI
| DE Program Sponsor | DE Program Owner | DE Leader | DE Team Members | DE Stakeholders
People & Roles | A | R | C |  | C
Engagement & Communication | A | R | C |  | C
Program Health & Assessment | A | R | C |  | C
Identify the Defects
Collect Information |  | A | R
Analyze the Information |  | A | R |  | C
Identify the Defects | I | A | R |  | C
Enter Defects into the Defect Register | I | A | R |  | I
Prioritize the Defects
Stakeholder Review of Defect Register |  | A | R |  | C
Assign Defect Priority |  | A | R |  | C
Gain Stakeholder Support | A | R | R
Analyze the Defects
Identify the DE Leader & DE Team Members | I | A | R |  | C
Collect the Defect Data | I | A | R | R | I
Problem Statement - Business Case - Objective Statement Development | I | A | R | R | I
Identify the Root Causes | I | A | R | R | I
Develop Solutions for the Defects
Identify Potential Solutions |  | A | R | R
Identify Solution Effectiveness & Priority |  | A | R | R
Choose Solutions for Implementation | I | A | R | R | C
Determine Measurement Plan | I | A | R | R | I
Implement the Solutions
Manage the Solution Implementation | I | A | R | R | C
Solution Implementation Progress Check | I | A | R | R | C
Verify and Sustain the Improvement
Track the Solution Effectiveness | I | A | R | R | C
Confirm Defect Is Eliminated with Stakeholders | I | A | R | R | C
Close Out the Defect in Defect Register | I | A | R | R | C
Celebrate and Communicate the Success | C | A | R | R | C

## R2L DE Process RACI
| DE Program Sponsor | DE Program Owner | DE Leader | DE Team Members | DE Stakeholders
People & Roles | A | R | C |  | C
Engagement & Communication | A | R | C |  | C
Program Health & Assessment | A | R | C |  | C
Identify the Defects
Collect Information |  | A | R
Review the Information and Identify the Defects |  | A | R |  | C
Enter Defects into the Defect Register | I | A | R |  | I
Prioritize the Defects
Assign Defect Priority |  | A | R |  | C
Stakeholder Review of Defect Register |  | A | R |  | C
Gain Stakeholder Support | A | R | R
Analyze the Defects
Identify the DE Leader & DE Team Members | I | A | R |  | C
Collect the Defect Data | I | A | R | R | I
Problem Statement - Business Case - Objective Statement Development | I | A | R | R | I
Identify the Root Causes | I | A | R | R | I
Develop Solutions for the Defects
Identify Potential Solutions |  | A | R | R
Choose Solutions for Implementation | I | A | R | R | C
Implement the Solutions
Manage the Solution Implementation | I | A | R | R | C
Solution Implementation Progress Check | I | A | R | R | C
Verify and Sustain the Improvement
Verify the Defect Is Eliminated and Close Out the Defect | I | A | R | R | C
Celebrate and Communicate the Success | C | A | R | R | C